## Tabelle1
ID | Epic | Description | Priority | Vertics | SP
1 | 0 | Bossfight Tutorial | !! | As a player I want to fight against the first boss, to further progress in the story. Furthermore I want to gain experience points and loot. | 3
2 | 0 | End Sequence Tutorial | ! | As a player I want to finish the first level. To do so I want to have a cut scene after the bossfight so I can make a progress in the storyline. | 3
3 | 0 | Implement Wodden Cabin | ! | As a player I want to move around in the cabin of the Adventurer. Furthermore I want to select different levels when I sit down in the rocking chair. | 3
4 | 0 | Cabin Level Screen | !! | As a player I want to select the different levels. Furthermore have a nice graphic design to get along with it. | 5
5 | 1 | Simple Level Structure of the first Level | !!! | As a player I want to move around in the second level. To progress in the story. | 5
6 | 1 | Design new Enemies | ! | As a Player I want to fight against 100 enemies. That means 10 new enemies per level. I also want to see some familiar enemies which I already met in previous games. | 5
7 | 1 | Convert Level form Paper to Unity | ! | As a player I want to have a good structured level, where I can move around freely and fight enemies. | 5
8 | 1 | Design Dialoges | ! | As a player I want to have interesting and hilarious dialoges between the characters. | 2
9 | 1 | Implement Questlog | ! | As a player I want to have a widget to access all my quests in order to have a good overview of all my open quests. Furthermore I want to get informed if a new quest comes up (Display Box for "You got a new Quest") | 5
10 | 1 | Old Lady Quest | !! | As a player I want to get the quest to help the old lady bring her "groceries" to her hut. | 5
11 | 1 | Hut of the old Lady | !! | As a player I want to see the hut of the old Lady. Furthermore I want to move around in it. | 2
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30