## Tabelle1
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
155 | 73 | 15 | 4.8667
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2017-04-27 | 9 |  | 3 | 9 | 155 | 0 | 3 | 0 | 155 | 0.33333
2017-05-04 | 11 |  | 0 | 11 | 155 | 3 | 3 | 9 | 155 | 0.15
2017-05-11 | 10 |  | 3 | 10 | 155 | 3 | 6 | 20 | 152 | 0.2
2017-05-18 | 9 |  | 0 | 9 | 152 | 6 | 6 | 30 | 152 | 0.15385
2017-05-25 | 9 |  | 0 | 9 | 152 | 6 | 6 | 39 | 152 | 0.125
2017-06-01 | 1 |  | 5 | 1 | 152 | 6 | 11 | 48 | 147 | 0.22449
2017-06-08 | 13 |  | 0 | 9 | 147 | 11 | 11 | 49 | 147 | 0.18966
2017-06-15 | 9 |  |  |  | 147 | 11 | 11 | 58 | 145.2931 | 0.18966
2017-06-22 | 9 |  |  |  | 145.2931 | 11 | 11 | 58 | 143.5862 | 0.18966
2017-06-29 | 14 |  |  |  | 143.5862 | 11 | 11 | 58 | 140.931 | 0.18966
2017-07-06 | 18 |  |  |  | 140.931 | 11 | 11 | 58 | 137.5172 | 0.18966
2017-07-13 | 13 |  |  |  | 137.5172 | 11 | 11 | 58 | 135.0517 | 0.18966
2017-07-20 | 10 |  |  |  | 135.0517 | 11 | 11 | 58 | 133.1552 | 0.18966
2017-07-27 | 10 |  |  |  | 133.1552 | 11 | 11 | 58 | 131.2586 | 0.18966
2017-08-03 | 7 |  |  |  | 131.2586 | 11 | 11 | 58 | 129.931 | 0.18966
2017-08-10 | 7 |  |  |  | 129.931 | 11 | 11 | 58 | 128.6034 | 0.18966
2017-08-17 | 7 |  |  |  | 128.6034 | 11 | 11 | 58 | 127.2759 | 0.18966
2017-08-24 | 5 |  |  |  | 127.2759 | 11 | 11 | 58 | 126.3276 | 0.18966
2017-08-31 | 5 |  |  |  | 126.3276 | 11 | 11 | 58 | 125.3793 | 0.18966
2017-09-07 | 5 |  |  |  | 125.3793 | 11 | 11 | 58 | 124.431 | 0.18966
2017-09-14 | 18 |  |  |  | 124.431 | 11 | 11 | 58 | 121.0172 | 0.18966
2017-09-21 | 18 |  |  |  | 121.0172 | 11 | 11 | 58 | 117.6034 | 0.18966
2017-09-28 | 18 |  |  |  | 117.6034 | 11 | 11 | 58 | 114.1897 | 0.18966
2017-10-05 | 18 |  |  |  | 114.1897 | 11 | 11 | 58 | 110.7759 | 0.18966
2017-10-12 | 18 |  |  |  | 110.7759 | 11 | 11 | 58 | 107.3621 | 0.18966
2017-10-19 | 18 |  |  |  | 107.3621 | 11 | 11 | 58 | 103.9483 | 0.18966
2017-10-26 | 18 |  |  |  | 103.9483 | 11 | 11 | 58 | 100.5345 | 0.18966
2017-11-02 | 18 |  |  |  | 100.5345 | 11 | 11 | 58 | 97.1207 | 0.18966
2017-11-09 | 18 |  |  |  | 97.1207 | 11 | 11 | 58 | 93.7069 | 0.18966
2017-11-16 | 18 |  |  |  | 93.7069 | 11 | 11 | 58 | 90.2931 | 0.18966
2017-11-23 | 18 |  |  |  | 90.2931 | 11 | 11 | 58 | 86.8793 | 0.18966
2017-11-30 | 18 |  |  |  | 86.8793 | 11 | 11 | 58 | 83.4655 | 0.18966
2017-12-07 | 18 |  |  |  | 83.4655 | 11 | 11 | 58 | 80.0517 | 0.18966
2017-12-14 | 18 |  |  |  | 80.0517 | 11 | 11 | 58 | 76.6379 | 0.18966
2017-12-21 | 18 |  |  |  | 76.6379 | 11 | 11 | 58 | 73.2241 | 0.18966
2017-12-28 | 18 |  |  |  | 73.2241 | 11 | 11 | 58 | 69.8103 | 0.18966
2018-01-04 | 18 |  |  |  | 69.8103 | 11 | 11 | 58 | 66.3966 | 0.18966
2018-01-11 | 18 |  |  |  | 66.3966 | 11 | 11 | 58 | 62.9828 | 0.18966
2018-01-18 | 18 |  |  |  | 62.9828 | 11 | 11 | 58 | 59.569 | 0.18966
2018-01-25 | 18 |  |  |  | 59.569 | 11 | 11 | 58 | 56.1552 | 0.18966
2018-02-01 | 18 |  |  |  | 56.1552 | 11 | 11 | 58 | 52.7414 | 0.18966
2018-02-08 | 21 |  |  |  | 52.7414 | 11 | 11 | 58 | 48.7586 | 0.18966
2018-02-15 | 21 |  |  |  | 48.7586 | 11 | 11 | 58 | 44.7759 | 0.18966
2018-02-22 | 21 |  |  |  | 44.7759 | 11 | 11 | 58 | 40.7931 | 0.18966
2018-03-01 | 21 |  |  |  | 40.7931 | 11 | 11 | 58 | 36.8103 | 0.18966
2018-03-08 | 21 |  |  |  | 36.8103 | 11 | 11 | 58 | 32.8276 | 0.18966
| 271 |  | 1.5714 | 8.2857
Formulas:
Open Story Points = [Open Story Points, row above]+7