## Tabelle1
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
117 | 49 | 200 | 0.245
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2017-04-27 | 9 |  | 3 | 9 | 117 | 0 | 3 | 0 | 117 | 0.33333
2017-05-04 | 11 |  | 0 | 11 | 117 | 3 | 3 | 9 | 117 | 0.15
2017-05-11 | 10 |  | 3 | 10 | 117 | 3 | 6 | 20 | 114 | 0.2
2017-05-18 | 9 |  | 0 | 9 | 114 | 6 | 6 | 30 | 114 | 0.15385
2017-05-25 | 9 |  | 0 | 9 | 114 | 6 | 6 | 39 | 114 | 0.125
2017-06-01 | 1 |  | 5 | 1 | 114 | 6 | 11 | 48 | 109 | 0.22449
2017-06-08 | 13 |  | 0 | 9 | 109 | 11 | 11 | 49 | 109 | 0.18966
2017-06-15 | 9 |  | 0 | 9 | 109 | 11 | 11 | 58 | 109 | 0.16418
2017-06-22 | 9 |  | 0 | 9 | 109 | 11 | 11 | 67 | 109 | 0.14474
2017-06-29 | 14 |  | 0 | 13 | 109 | 11 | 11 | 76 | 109 | 0.1236
2017-07-06 | 18 |  | 0 | 13 | 109 | 11 | 11 | 89 | 109 | 0.10784
2017-07-13 | 13 |  | 0 | 9 | 109 | 11 | 11 | 102 | 109 | 0.099099
2017-07-20 | 10 |  | 0 | 10 | 109 | 11 | 11 | 111 | 109 | 0.090909
2017-07-27 | 10 |  | 0 | 10 | 109 | 11 | 11 | 121 | 109 | 0.083969
2017-08-03 | 7 |  | 0 | 7 | 109 | 11 | 11 | 131 | 109 | 0.07971
2017-08-10 | 7 |  | 0 | 0 | 109 | 11 | 11 | 138 | 109 | 0.07971
2017-08-17 | 7 |  | 0 | 7 | 109 | 11 | 11 | 138 | 109 | 0.075862
2017-08-24 | 5 |  | 3 | 5 | 109 | 11 | 14 | 145 | 106 | 0.093333
2017-08-31 | 5 |  | 0 | 5 | 106 | 14 | 14 | 150 | 106 | 0.090323
2017-09-07 | 5 |  | 0 | 5 | 106 | 14 | 14 | 155 | 106 | 0.0875
2017-09-14 | 18 |  | 5 | 18 | 106 | 14 | 19 | 160 | 101 | 0.10674
2017-09-21 | 18 |  | 12 | 20 | 101 | 19 | 31 | 178 | 89 | 0.15657
2017-09-28 | 18 |  | 0 | 18 | 89 | 31 | 31 | 198 | 89 | 0.14352
2017-10-05 | 18 |  | 5 | 18 | 89 | 31 | 36 | 216 | 84 | 0.15385
2017-10-12 | 18 |  | 0 | 18 | 84 | 36 | 36 | 234 | 84 | 0.14286
2017-10-19 | 18 |  | 0 | 18 | 84 | 36 | 36 | 252 | 84 | 0.13333
2017-10-26 | 18 |  | 0 | 18 | 84 | 36 | 36 | 270 | 84 | 0.125
2017-11-02 | 18 |  | 0 | 18 | 84 | 36 | 36 | 288 | 84 | 0.11765
2017-11-09 | 18 |  | 5 | 18 | 84 | 36 | 41 | 306 | 79 | 0.12654
2017-11-16 | 18 |  | 5 | 18 | 79 | 41 | 46 | 324 | 74 | 0.1345
2017-11-23 | 18 |  |  |  | 74 | 46 | 46 | 342 | 71.5789 | 0.1345
2017-11-30 | 18 |  |  |  | 71.5789 | 46 | 46 | 342 | 69.1579 | 0.1345
2017-12-07 | 18 |  |  |  | 69.1579 | 46 | 46 | 342 | 66.7368 | 0.1345
2017-12-14 | 18 |  |  |  | 66.7368 | 46 | 46 | 342 | 64.3158 | 0.1345
2017-12-21 | 18 |  |  |  | 64.3158 | 46 | 46 | 342 | 61.8947 | 0.1345
2017-12-28 | 18 |  |  |  | 61.8947 | 46 | 46 | 342 | 59.4737 | 0.1345
2018-01-04 | 18 |  |  |  | 59.4737 | 46 | 46 | 342 | 57.0526 | 0.1345
2018-01-11 | 18 |  |  |  | 57.0526 | 46 | 46 | 342 | 54.6316 | 0.1345
2018-01-18 | 18 |  |  |  | 54.6316 | 46 | 46 | 342 | 52.2105 | 0.1345
2018-01-25 | 18 |  |  |  | 52.2105 | 46 | 46 | 342 | 49.7895 | 0.1345
2018-02-01 | 18 |  |  |  | 49.7895 | 46 | 46 | 342 | 47.3684 | 0.1345
2018-02-08 | 21 |  |  |  | 47.3684 | 46 | 46 | 342 | 44.5439 | 0.1345
2018-02-15 | 21 |  |  |  | 44.5439 | 46 | 46 | 342 | 41.7193 | 0.1345
2018-02-22 | 21 |  |  |  | 41.7193 | 46 | 46 | 342 | 38.8947 | 0.1345
2018-03-01 | 21 |  |  |  | 38.8947 | 46 | 46 | 342 | 36.0702 | 0.1345
2018-03-08 | 21 |  |  |  | 36.0702 | 46 | 46 | 342 | 33.2456 | 0.1345
| 271 |  | 1.5333 | 11.4
Formulas:
Open Story Points = [Open Story Points, row above]+7