## Tabelle1
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
122 | 49 | 200 | 0.245
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2017-04-27 | 9 |  | 3 | 9 | 122 | 0 | 3 | 0 | 122 | 0.33333
2017-05-04 | 11 |  | 0 | 11 | 122 | 3 | 3 | 9 | 122 | 0.15
2017-05-11 | 10 |  | 3 | 10 | 122 | 3 | 6 | 20 | 119 | 0.2
2017-05-18 | 9 |  | 0 | 9 | 119 | 6 | 6 | 30 | 119 | 0.15385
2017-05-25 | 9 |  | 0 | 9 | 119 | 6 | 6 | 39 | 119 | 0.125
2017-06-01 | 1 |  | 5 | 1 | 119 | 6 | 11 | 48 | 114 | 0.22449
2017-06-08 | 13 |  | 0 | 9 | 114 | 11 | 11 | 49 | 114 | 0.18966
2017-06-15 | 9 |  | 0 | 9 | 114 | 11 | 11 | 58 | 114 | 0.16418
2017-06-22 | 9 |  | 0 | 9 | 114 | 11 | 11 | 67 | 114 | 0.14474
2017-06-29 | 14 |  | 0 | 13 | 114 | 11 | 11 | 76 | 114 | 0.1236
2017-07-06 | 18 |  | 0 | 13 | 114 | 11 | 11 | 89 | 114 | 0.10784
2017-07-13 | 13 |  | 0 | 9 | 114 | 11 | 11 | 102 | 114 | 0.099099
2017-07-20 | 10 |  | 0 | 10 | 114 | 11 | 11 | 111 | 114 | 0.090909
2017-07-27 | 10 |  | 0 | 10 | 114 | 11 | 11 | 121 | 114 | 0.083969
2017-08-03 | 7 |  | 0 | 7 | 114 | 11 | 11 | 131 | 114 | 0.07971
2017-08-10 | 7 |  | 0 | 0 | 114 | 11 | 11 | 138 | 114 | 0.07971
2017-08-17 | 7 |  | 0 | 7 | 114 | 11 | 11 | 138 | 114 | 0.075862
2017-08-24 | 5 |  | 3 | 5 | 114 | 11 | 14 | 145 | 111 | 0.093333
2017-08-31 | 5 |  | 0 | 5 | 111 | 14 | 14 | 150 | 111 | 0.090323
2017-09-07 | 5 |  | 0 | 5 | 111 | 14 | 14 | 155 | 111 | 0.0875
2017-09-14 | 18 |  | 5 | 18 | 111 | 14 | 19 | 160 | 106 | 0.10674
2017-09-21 | 18 |  | 12 | 20 | 106 | 19 | 31 | 178 | 94 | 0.15657
2017-09-28 | 18 |  | 0 | 18 | 94 | 31 | 31 | 198 | 94 | 0.14352
2017-10-05 | 18 |  | 5 | 18 | 94 | 31 | 36 | 216 | 89 | 0.15385
2017-10-12 | 18 |  | 0 | 18 | 89 | 36 | 36 | 234 | 89 | 0.14286
2017-10-19 | 18 |  | 0 | 18 | 89 | 36 | 36 | 252 | 89 | 0.13333
2017-10-26 | 18 |  | 0 | 18 | 89 | 36 | 36 | 270 | 89 | 0.125
2017-11-02 | 18 |  | 0 | 18 | 89 | 36 | 36 | 288 | 89 | 0.11765
2017-11-09 | 18 |  | 5 | 18 | 89 | 36 | 41 | 306 | 84 | 0.12654
2017-11-16 | 18 |  | 10 | 18 | 84 | 41 | 51 | 324 | 74 | 0.14912
2017-11-23 | 18 | -44 | 3 | 18 | 30 | 51 | 54 | 342 | 27 | 0.15
2017-11-30 | 18 |  |  | 18 | 27 | 54 | 54 | 360 | 24.3 | 0.15
2017-12-07 | 18 |  |  | 18 | 24.3 | 54 | 54 | 378 | 21.6 | 0.15
2017-12-14 | 0 |  |  | 0 | 21.6 | 54 | 54 | 396 | 21.6 | 0.15
2017-12-21 | 18 |  |  | 12 | 21.6 | 54 | 54 | 396 | 18.9 | 0.15
2017-12-28 | 10 |  |  | 0 | 18.9 | 54 | 54 | 408 | 17.4 | 0.15
2018-01-04 | 10 |  |  | 0 | 17.4 | 54 | 54 | 408 | 15.9 | 0.15
2018-01-11 | 18 |  |  | 12 | 15.9 | 54 | 54 | 408 | 13.2 | 0.15
2018-01-18 | 18 |  |  | 18 | 13.2 | 54 | 54 | 420 | 10.5 | 0.15
2018-01-25 | 18 |  |  | 18 | 10.5 | 54 | 54 | 438 | 7.8 | 0.15
2018-02-01 | 18 |  |  |  | 7.8 | 54 | 54 | 456 | 5.1 | 0.15
2018-02-08 | 21 |  |  |  | 5.1 | 54 | 54 | 456 | 1.95 | 0.15
2018-02-15 | 21 |  |  |  | 1.95 | 54 | 54 | 456 | 0 | 0.15
2018-02-22 | 21 |  |  |  | 0 | 54 | 54 | 456 | 0 | 0.15
2018-03-01 | 21 |  |  |  | 0 | 54 | 54 | 456 | 0 | 0.15
2018-03-08 | 21 |  |  |  | 0 | 54 | 54 | 456 | 0 | 0.15
2018-03-15 | 21 |  |  |  | 0 | 54 | 54 | 456 | 0 | 0.15
2018-03-22 | 21 |  |  |  | 0 | 54 | 54 | 456 | 0 | 0.15
2018-03-29 | 21 |  |  |  | 0 | 54 | 54 | 456 | 0 | 0.15
| 271 |  | 1.7419 | 11.4
Formulas:
Open Story Points = [Open Story Points, row above]+7