## Tabelle1
Task | Orig. Est. (h) | Curr. Est. (h) | Effort (h) | Remain(h) | Responsible | Completion (%) | Completed | User Stoy ID | Datum | Notes
Revision of Inventory System (more Automatically) | 6 | 2.5 | 1 | 1.5 | Oguz | 40% | X |  |  | Aufgabe auf Sascha übertragen.
Automatic Pick-Up for Inventory | 6 | 5.5 | 2 | 3.5 | Oguz | 36.36% | X |  |  | Aufgabe auf Sascha übertragen.
Inventory for chest | 3 | 2 | 0 | 2 | Oguz | 0% | X |  |  | Aufgabe auf Sascha übertragen.
Finish Enemie Minotaurus Sprite | 1 | 1.5 | 1.5 | 0 | Cedric | 100% | ✔
Fighting Animation for Weapons (Axe) | 3 | 6 | 6 | 0 | Cedric | 100% | ✔ | 35
Complete Cave Level for Tutorial | 1 | 2 | 2 | 0 | Sascha | 100% | ✔ | 37
Creating AI for Slime Mob (Walking) | 3 | 6 | 6 | 0 | Sascha | 100% | ✔ | 34
Some Bugfixing for Changing the Scene (UI, Player, …) | 2 | 1.5 | 1.5 | 0 | Sascha | 100% | ✔ | 37 |  | Player changing scene is working UI and GUI has to pe implemented
Secret for Cave | 2 | 2 | 2 | 0 | Sascha | 100% | ✔ |  |  | Secret shows up after the slime is defeated
Bugfixing for Spritesheet for the player fighting with an axe | 3 | 3 | 3 | 0 | Cedric | 100% | ✔ | 35
Slime Gag einbauen + Tutorial Level weiterbauen | 3 | 3 |  | 3 | Sascha | 0% | X |  |  | [ENEMIE] Fliege Slime: Fliegt nach Boss-Einleitung weg, fällt eventuell am Ende des Spiels auf den Endboss und dadurch wird Phase 2 Eingeleitet.
Gold Drop form enemy after he is defeated | 6 | 6 |  | 6 | Oguz | 0% | X
Add Secret Sound for Cave Secret + Compose | 3 | 3 | 3 | 0 | Sascha | 100% | ✔
Bugfix Slime AI for Edges | 2 | 2 | 2 | 0 | Sascha | 100% | ✔ | 34 |  | Slimes tend to slide down the Edges insted of jumping over them
Spritesheet for first Boss (tree with witch) + Squirel Spritesheet | 3 | 3 | 3 | 0 | Cedric | 100% | ✔ | 1
Basic Inventory System + Inventory Sheet | 3 | 9 | 9 | 0 | Sascha | 100% | ✔ | 33 |  | Basic Inventory Sastem for the Game (Aufgabevon Oguz auf Sascha übertragen)
Advanced Inventory (e.g.: Pop-Up on Moseover, Item Selection, ...) | 6 | 9 | 9 | 0 | Sascha | 100% | ✔ | 33
Source Tree + GitHub configured | 2 | 3 | 3 | 0 | Sascha, Cedric | 100% | ✔
Implementation of First Boss ("Witch Tree") with Squirel | 10 | 10 | 10 | 0 | Sascha | 100% | ✔ | 1
Combatsystem for Axe | 6 | 6 | 6 | 0 | Cedric | 100% | ✔ | 35
Bugfixing | 3 | 3 | 3 | 0 | Sascha | 100% | ✔ |  |  | Bugfixing siehe Bugs.xlsx Didn't fixed all Bugs
Sprite for Jumping | 3 | 3 | 3 | 0 | Cedric | 100% | ✔ | 30
Axe in the Stone for Cave | 9 | 9 | 9 | 0 | Sascha | 100% | ✔ | 37
Health UI for Enemies | 6 | 6 | 6 | 0 | Cedric | 100% | ✔ | 35
Sprite für Schweinchenhexe | 1 | 1 | 1 | 0 | Steffi | 100% | ✔ | 19
Hexenhütte | 2.5 | 2.5 | 2.5 | 0 | Steffi | 100% | ✔ | 20
Iphi Sprite + Animation | 2.5 | 6 | 2.5 | 3.5 | Steffi | 41.67% | X | 7
End Sequence for first Level + Include Adventurer in Rocker | 4 | 4 | 4 | 0 | Sascha | 100% | ✔ | 3
Rotation of the player by Mouse Movement Fix | 1 | 1 | 1 | 0 | Cedric | 100% | ✔ | 30
SquirrelWurf Skript | 3 | 3 | 3 | 0 | Cedric | 100% | ✔ | 1
Implement General Boss Healthbar | 3 | 3 | 3 | 0 | Cedric | 100% | ✔ | 1
Villager Sprites (15) | 6 | 6 | 6 | 0 | Steffi | 100% | ✔ | 9
Flicker Script for Hut of Adventurer | 2 | 2 | 2 | 0 | Sascha | 100% | ✔ | 3
Basic Level Selection for Inside of Hut + Implement dynamic Square for Level Selection | 3 | 5 | 5 | 0 | Sascha | 100% | ✔ | 4 |  | The square should be dynamicly arranged around the artifacts which are used to select the level
Knockback revisited | 2 | 2 | 2 | 0 | Cedric | 100% | ✔ | 35
Walk + Run Animation for Adventurer | 3 | 3 | 4 | 0 | Steffi | 100% | ✔ | 8
Village Sprite (Intro) | 5 | 5 | 5 | 0 | Steffi | 100% | ✔ | 9
Bugfixing for Stoney | 1 | 0.5 | 0.5 | 0 | Sascha | 100% | ✔ | 37
Finish Building of Tutorial Level | 0.5 | 0.5 | 0.5 | 0 | Sascha | 100% | ✔ | 30
Add Firewood and let it drop from the Boss | 2 | 2 | 2 | 0 | Sascha | 100% | ✔ | 42
Rework of Start Sequence | 1 | 2 | 2 | 0 | Sascha | 100% | ✔ | 39
Credits | 0.5 | 0.25 | 0.25 | 0 | Sascha | 100% | ✔ | 43
Background for Main Menu | 1 | 1 | 1 | 0 | Steffi | 100% | ✔ | 44
Bugfixing for Player getting stuck on the Witchtree/Walls | 2 | 4 | 4 | 0 | Cedric | 100% | ✔ | 25
Design and drawing of new enemies | 4 | 4 | 4 | 0 | Steffi | 100% | ✔ | 30
Bugfixing for Tutorial Level | 0.5 | 0.5 | 0.5 | 0 | Cedric | 100% | ✔ | 25
XML Reader(Load Dialoges form XML) | 5 | 10 | 10 | 0 | Sascha | 100% | ✔ | 47
Design/Pixel of independent sprites | 8 | 8 | 8 | 0 | Steffi | 100% | ✔ | 30
Add additional attack for first boss | 6 | 10 | 10 | 0 | Cedric | 100% | ✔ | 42
Implementing XML Reader for all Dialoges | 3 | 4 | 4 | 0 | Sascha | 100% | ✔ | 47
Landscape sprites/tiles | 6 | 6 | 6 | 0 | Steffi | 100% | ✔ | 30
Porky(enemy) implementation in game | 5 | 5 | 2 | 3 | Sascha | 40% | X | 13
Bat enemy implementation | 4 | 4 | 0 | 4 | Cedric | 0% | X | 13
Implement first level (Basic Colliders, "Decoration") | 3 | 3 |  | 3 | Cedric, Sascha | 0% | X | 13
Design and draw Sprite for "Vanishing Hill" | 1 | 1 | 1 | 0 | Steffi | 100% | ✔ | 10
Implementation of "Vanishing Hill" | 2 | 3 | 2 | 1 | Sascha | 66.67% | X | 10
Drawing new Background for second Level | 2 | 2 | 2 | 0 | Steffi | 100% | ✔ | 10
Drawing Clouds for the second Level | 2 | 2 | 2 | 0 | Steffi | 100% | ✔ | 10
Implementing scrolling of the Clouds | 3 | 3 | 3 | 0 | Sascha | 100% | ✔ | 10
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!
|  |  |  | 0 |  | #DIV/0! | #DIV/0!