## Tabelle1
ID | Epic | Description | Priority | Vertics | SP
1 | 0 | Bossfight Tutorial | !! | Throw Script | 3
2 | 0 | End Sequence Tutorial | ! | Start trigger, Dialoge, Walk Back scene | 3
3 | 0 | Implement Wodden Cabin | ! | Add Sprite to Level, Add Colliders, add door, add intro squence | 3
4 | 0 | Cabin Level Screen | !! | Select frame, trophys for levels, animations for characters and "living" objects, entry dialoge | 5
5 | 1 | Simple Level Structure of the second Level | !!! | Landscape on paper, mark position of enemies secrets treasures and entrances, check if choises are possible in unity | 5
6 | 1 | Design new Enemies | ! | Movement, spawn location, atack movement, stats, special actions (e.g. poision), Design Basic Sprite | 5
7 | 1 | Convert Level form Paper to Unity | ! | Basic level plan to unity with colliders and sprites | 5
8 | 1 | Design Dialoges | ! | Write a basic script for the dialoge the people say. | 2
9 | 1 | Implement Questlog | ! | GUI to manage all the Quests the player gets, Display Box for "You got a new Quest" | 5
10 | 1
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30