## Tabelle1
ID | Epic | Description | Priority | Vertics | SP | Finished
1 | 0 | Bossfight Tutorial | !! | As a player I want to fight against the first boss, to further progress in the story. Furthermore I want to gain experience points and loot. | 3 | ok | 171
2 | 0 | End Sequence Tutorial | ! | As a player I want to finish the first level. To do so I want to have a cut scene after the bossfight so I can make a progress in the storyline. | 3 | ok
3 | 0 | Implement Wodden Cabin | ! | As a player I want to move around in the cabin of the Adventurer. Furthermore I want to select different levels when I sit down in the rocking chair. | 3 | ok
4 | 0 | Cabin Level Screen | !! | As a player I want to select the different levels. Furthermore have a nice graphic design to get along with it. | 5 | ok
5
6 | 1 | Iphrit | ! | As a player I want to see a nice looking sprite of the second boss. I also want to see him moving and fight against him. | 5
7 | 1 | Start Sequence for second level | !! | As a player I want to see a sequence why the player gets out of his hut to investigate whats going on. And I also want to see a sequence how the player gets to the town. | 3
8 | 1 | Villagers running | ! | As a player I want to see the villagers running by the hut of the Adventurer. Furthermore I want to hear an explanation why they are running away. | 1
9 | 1 | Implement Questlog | ! | As a player I want to have a widget to access all my quests in order to have a good overview of all my open quests. Furthermore I want to get informed if a new quest comes up (Display Box for "You got a new Quest") | 5
10 | 1 | Simple Level Structure of the second Level (City) | !!! | As a player I want to move around in the second level. To progress in the story. I as well want to move arround in a nice looking city. Furthermore there must be some enemies which I can fight against. | 5 | ok
11 | 1 | Witch Sequence | !! | As a player I want to see a sequence why I have to fight against Iphrit. As a player I also want to see how I get sent back in time after I lost agianst Iphrit | 3
12 | 1 | Design new Enemies | ! | As a Player I want to fight against 100 different enemy types. That means 10 new enemies per level. I also want to see some familiar enemies which I already met in previous games. | 8
13 | 1 | Create second part of first level (Past) |  | As a player I want to move arround in the forest which leads to the town. | 5
14 | 1 | Convert Level form Paper to Unity | ! | As a player I want to have a good structured level, where I can move around freely and fight enemies. | 3
15 | 1 | Create Old Lady sequence |  | As a player I want to see why I go to the hut of the old lady. | 2
16 | 1 | Design Dialoges | ! | As a player I want to have a dialoges between the adventurer and the old lady. | 2
17 | 1 | Old Lady Quest | !! | As a player I want to get the quest to help the old lady bring her "groceries" to her hut. | 5
18 | 1 | Sprite for the inside of the hut for the old lady + implementation |  | As a player I want to see a nice looking sprite of the inside of the old lady's hut | 3
19 | 1 | Hut of the old Lady | !! | As a player I want to see the hut of the old Lady. Furthermore I want to move around in it. | 2
20 | 1 | Sequence for the inside of the hut of the old lady | !!! | As a player I want to see a sequence why the old lady is a witch and how she gets turned into a pig | 3
21 | 1 | Riding pig to town | !! | As a player I want to ride to the town on the pig. | 5
22 | 1 | City Gate | !!! | As a player I want to see a sprite for the city gate.Furthermore I want to see two guards (chubby and thin). I also want to hear why they don't let me in town and how I can get into town. | 3
23 | 1 | Design way to the nest | !! | As a player I want to have a short way I can walk to get to the nest of the beast. | 3
24 | 1 | Design and implement the first-mini boss | !!! | As a player I want to fight against the first mini-boss. After I have defeated him, I want to get an artifact | 8
25 | 0 | Physics | !!! | As a player I want to have realistic physics. Furthermore I want to move arround without getting caught somewhere | 5 | ok
26 | 0 | Main Menu | !! | As a player I want to have a working Main Menu, which starts the Game, Gives me the Option to load my saved Game and choose between some simple options. | 5
27 | 0 | Camera | !!! | As a player I want to see the game and have accurate camera movement which for example followes me. | 2 | ok
28 | 0 | Sprite for Player | !!! | As a player I want to see a sprite for the Adventurer. Furthermore I want it to be fluently animated. | 3 | ok
29 | 0 | Movement of Player | !!! | As a player I want to move the Adventurer around. Furthermore I want the Adventurer to be able to (double) jump. I also want the Adventurer to rotate according to my mouse movement. | 5 | ok
30 | 0 | Sprites for the first Level + Layout of the first level | !!! | As a player I want to see the ground sprites for the first level. Furthermore I want an enviroment in which I can move around. | 5 | ok
31 | 0 | Background for first Level | ! | As a player I want to see the forest in the background of the first level. | 2 | ok
32 | 0 | Inventory | !! | As a player I want to see a UI for the inventory. Furthermore I want to drag around items, use them and see informations about them when I hover over them. | 8 | ok
33 | 0 | Slime Enemy | !! | As a player I want to fight against a slime. This slime has to have a sprite and movement when he des not attack. Furthermore I want the slime to attack me when I come near it | 3 | ok
34 | 0 | Fighting + UI | !! | As a player I want to see an indicator on how much health an enemy has. Furthermore I want it to be animated. | 8 | ok
35 | 0 | Chest | !! | As a player I want to have a sprite and a sound for a chest. Furthermore I want to get an item out of it when I am opening it. | 3 | ok
36 | 0 | Excalibur Cave | !!! | As a palyer I want to see an enviroment for the cave. Furthermore, I want to move around in it. | 2 | ok
37 | 0 | Excalibur Cut Scene | !!! | As a player I want to see a cutscene how I get the axe from Excalibur and why he doesn't want me to receive it. | 3 | ok
38 | 0 | Esc Menu | !! | As a player I want to see a menu when I press Esc which gives me some simple options. Furthermore I want it to disappear when I press Esc again. | 1 | ok
39 | 0 | Intro Sequence for Game | !!! | As a player I want to see a cutscene when the game starts. It gives me an introduction to the game. | 2 | ok
40 | 0 | Game UI | !!! | As a player I want to see an UI which displays my current health. Furthermore, I want to see Icons that show which buttons I have to press in order to do specific actions. | 5 | ok
41 | 0 | Event List | !!! | As a player I want a List, where events are listed, so they don't accour again. | 2 | ok
42 | 0 | Firewood Drop fom Witchboss | !!! | As a player I want to get "Firewood" when I defeat the Witchtree | 2 | ok
43 | 0 | Credits | ! | As a player I want to see who made the game and their Functions | 1 | ok
44 | 0 | Background for Main Menu | ! | As a Player I want to have a nice looking Background while I am in the Main Menu | 1 | ok
45 | -
46 | 1 | Background/Sprites for first part of Level 1 | !!! | As a player I want to be able to see the ground of the first part of level 1 to walk on. Also, I want to see the background and the objects. | 5 | ok
47 | 1 | Write an XMLReader for the ingame dialogues | !! | As a player I want to be able to read the dialogues of the game. This should be accomplished with a simple XMLReader. | 5 | ok
48 | 1 | Extended Tutorial Bossfight | !! | As a player I want the first boss I fight against to be able to use multiple different attacks instead of just one. | 5 | ok
49 | 1
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71